## Sheet1
|  | SPRINT 1 |  | SPRINT2
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Remaining Effort | 65 | 51 | 32 | 20 | 18 | 0
Ideal Burndown | 65 | 48.5 | 32 | 15.5 | 0